## Sheet1
Woodland Joint Unified School District
Adult Education CTE Classroom Renovations PROJECT No: 2023-02-3
PROJECT SCHEDULE | Updated: 3/20/2023 VP
Submit advertisement (Local newspaper/Builders Exchange) | 2023-02-28
First Advertisement | 2023-03-02
Second Advertisement | 2023-03-09
Mandatory Pre-Bid Walk @ 10AM Meet front of school | 2023-03-13
Final Day to Submit RFIs | 2023-03-24
Final Day for Addendum | 2023-03-30
Bid Opening (HB) (12PM) | 2023-04-05
Upload bid results - District page | 2023-04-06
Submit board packet | 2023-04-14
Tentative Board Approval (Lowest hard bid) | 2023-04-27
Award Contract | 2023-05-01
Construction Meeting | 2023-05-05
Construction | May-July
Job walk - Punch list | 2023-07-24
Project Completion/Occupancy - (first day of school 8/14/23) | 2023-08-04